## Sheet1
RE- FINISH OF non flapped 15m sailplane
SUMMARY based on actual times recorded on LS-1
Note: this aircraft had previously been re-finished using a polyester Gel-coat
maybe
TIMES FOR: | HOURS | needed | miimum
| recorded | or optional | ever
FUSELAGE | 123 | 48 | 75
0
CANOPY | 28 | 19 | 9
0
PORT WING | 131.25 | 54.5 | 76.75
0
STBD WING | 131.25 | 54.5 | 76.75
0
RUDDER | 15.2 | 1.7 | 13.5
0
AILERONS - BOTH | 26.2 | 0 | 26.2
0
TAILPLANE | 14.6 | 3.2 | 11.4
0
ELEVATOR | 10.1 | 3.5 | 6.6
0
ANNUAL INSPECTION + airworthiness items | 25.5 | 25.5 | 0
0
TRAILER | 4 | 4 | 0
0
TOTAL HOURS BOOKED / OPTIONAL and MIN. LIKELY | 509.1 | 213.9 | 295.2
MATERIALS |  | 2060
PARTS in this case re-furbished release and all seals | 550 | 550 | 0
FUSELAGE
unload, position in shop | 2
remove cockpit equipment | 2 | 2
remove old layers of paint - gel-coat | 26 | 10
remove old tailskid | 0.5
apply first coat of high build primer | 6
sand out first coat of primer - no details 60 grit | 4
apply second coat of high build primer | 4 | 4
sand out second coat of primer - some detailing | 6 | 6
apply third coat of primer | 4 | 4
repair and improve fit on gear doors | 4 | 4
sand out third coat of primer with 120 | 4 | 4
deal with "pin holes" | 4
minor contouring over factory seams etc | 4
sand out ready for first top coat with 220 | 8
apply first top coat | 6
sand out first top coat 220 grit | 6
apply second top coat | 6 | 6
sand out second top coat 320 grit | 4 | 4
touch ups and pin holes | 4
finish sand 400 | 3
finish sand 600 | 3
finish sand 2000 | 2
buff and clean | 4
clean cockpit | 2
re-install instruments, plumbing, wiring, improve routing | 4 | 4
re- install new tailskid | 0.5
TOTAL FOR FUSELAGE | 123 | 48
0
CANOPY + RAILS ETC
protect outside (spraylat) | 1 | 1
protect inside (spraylat) | 2
clean off old seals and adhesive | 1 | 1
adjust hardware for better fit | 1.5 | 1.5
remove old gelcoat from canopy outside | 1.5 | 1.5
fair fuselage and canopy together again | 4 | 4
prepare fuselage portion of canopy rail apply gel-coat | 2 | 2
close large gap between canopy and fuselage on sides | 4 | 4
fill and fair canopy rim ready for first white | 2
mask and apply first white on canopy rim | 2
sand fix and prepare for second white on canopy rim | 2
prepare inside of canopy rim for improvement of looks | 2 | 2
paint inside of canopy rim | 1 | 2
remove protective inside and outside "Spraylat", remove tape
residue and clean acrylic, re-install vent window | 2
TOTAL FOR CANOPY | 28 | 19
CONTROLS
Rudder
weight and balance as received | 1 | 0.5
remove existing layers of gel-coat | 2
serious glass repairs - old repairs to fix | 4 | 4
apply first top coat as primer | 2
sand out first top coat | 2
apply second top coat -deal with pin holes | 2
sand out second top coat - touch ups | 2
finish sand with 400 | 1
finish sand with 600 | 0.6
finish sand with 2000 | 0.6
buff and polish | 0.4
weight and balance as finished | 0.4
apply all seals | 1.2 | 1.2
TOTAL FOR RUDDER (excluding repairs) | 15.2 | 1.7
Tailplane
weigh as received | 0.2 | 0.2
remove existing layers of gel-coat | 4
apply primer | 1.5
sand out primer 80 grit first time | 1.5
apply primer second time | 1.5 | 1.5
sand out second primer | 1.5 | 1.5
apply top coat | 1
first sand out 320 or 220 W&D | 1
finish sand with 400 | 0.6
finish sand with 600 | 0.6
finish sand with 2000 | 0.6
buff and polish | 0.4
weigh as finished | 0.2
TOTAL FOR TAILPLANE | 14.6 | 3.2
Elevator
weight and balance as received | 0.5
remove existing layers of gel-coat | 2.5 | 1
minor glass repairs trailing edge (TE) | 0.5 | 0.5
apply first top coat as primer | 0.5
sand out first top coat | 1
apply second top coat -deal with pin holes | 0.5
sand out second top coat - touch ups | 1
finish sand with 400 | 0.4
finish sand with 600 | 0.4
finish sand with 2000 | 0.3
buff and polish | 0.2
weight and balance as finished | 0.3
apply all seals | 2 | 2
TOTAL FOR ELEVATOR | 10.1 | 3.5
Port aileron
weight and balance as received | 0.5
remove existing layers of gel-coat | 4
minor glass repairs trailing edge (TE) | 0.5
apply first top coat as primer | 1
sand out first top coat | 1.5
apply second top coat -deal with pin holes | 1.5
sand out second top coat - touch ups | 1.5
finish sand with 400 | 1
finish sand with 600 | 0.6
finish sand with 2000 | 0.4
buff and polish | 0.3
weight and balance as finished | 0.3
Stbd aileron
weight and balance as received | 0.5
remove existing layers of gel-coat | 4
minor glass repairs trailing edge (TE) | 0.5
apply first top coat as primer | 1
sand out first top coat | 1.5
apply second top coat -deal with pin holes | 1.5
sand out second top coat - touch ups | 1.5
finish sand with 400 | 1
finish sand with 600 | 0.6
finish sand with 2000 | 0.4
buff and polish | 0.3
weight and balance as finished | 0.3
TOTAL FOR BOTH AILERONS | 26.2
Port wing
unload, position in shop | 2
remove old layers of paint - gel-coat | 25.75 | 9
remove "loose" factory gel-caot Note: Shiny areas | 5 | 4
minor repairs - stabilize and contour "depressions" | 2 | 1
Dive brake related work- see note: Dive brakes | 9.5 | 4
contouring at wing roots both surfaces | 2.5 | 2.5
minor contouring over factory seams, TE & LEedge etc. | 2 | 1
leading edge deal with voids etc. | 1.5
final prep. for first primer, masking, wipe down etc. | 1.5
apply first coats of high build primer | 4
sand out first coat of primer - no details 60 grit | 7
sand out first coat of primer 80 grit no details | 9 | 9
final prep. for second primer, masking, wipe down etc. | 1.5 | 1.5
apply second coat of high build primer Note: Contours | 7 | 7
sand out second coat of primer - some detailing | 6 | 6
deal with "pin holes" | 1.5
sand out ready for first top coat with 220 | 4
prepare shop and wing for first top coat, clean, mask etc. | 4
apply first top coat - many coats to avoid second application | 6
sand out first top coat 320 wet | 3
deal with "fish eyes" "pin holes" minor touch ups incl. DB | 6 | 3
sand out with 400 wet | 4 | 1
sand out with 600 wet | 4 | 1
sand out with 2000 wet | 3
buff and clean | 3
clean and lubricate hinge pins and bushings, instal aileron | 2
install inspection plate and new wing tip skid | 1.5 | 1.5
install all seals | 3 | 3
TOTAL FOR PORT WING | 131.25 | 54.5
STBD WING
unload, position in shop | 2
remove old layers of paint - gel-coat | 25.75 | 9
remove "loose" factory gel-caot Note: Shiney areas | 5 | 4
minor repairs - stabilize and contour "depressions" | 2 | 1
Dive brake related work- see note: Dive brakes | 9.5 | 4
contouring at wing roots both surfaces | 2.5 | 2.5
minor contouring over factory seams, TE & LEedge etc. | 2 | 1
leading edge deal with voids etc. | 1.5
final prep. for first primer, masking, wipe down etc. | 1.5
apply first coats of high build primer | 4
sand out first coat of primer - no details 60 grit | 7
sand out first coat of primer 80 grit no details | 9 | 9
final prep. for second primer, masking, wipe down etc. | 1.5 | 1.5
apply second coat of high build primer Note: Contours | 7 | 7
sand out second coat of primer - some detailing | 6 | 6
deal with "pin holes" | 1.5
sand out ready for first top coat with 220 | 4
prepare shop and wing for first top coat, clean, mask etc. | 4
apply first top coat - many coats to avoid second application | 6
sand out first top coat 320 wet | 3
deal with "fish eyes" "pin holes" minor touch ups incl. DB | 6 | 3
sand out with 400 wet | 4 | 1
sand out with 600 wet | 4 | 1
sand out with 2000 wet | 3
buff and clean | 3
clean and lubricate hinge pins and bushings, instal aileron | 2
install inspection plate and new wing tip skid | 1.5 | 1.5
install all seals | 3 | 3
TOTAL STBD WING | 131.25 | 54.5
Annual inspection and corrective messures
Dive brake bushings frozen in one wing, ream replace | 5 | 5 |  |  | 10
Note: cost of tools and replacement bushings exceed charge
change rudder pedal adjustment cable to stainless | 1 | 1
change release cable to stainless | 0.5 | 0.5
install new release | 2 | 2
"invent" and install new brake system | 8 | 8
fabricate and install new under wing inspection covers | 2 | 2
remove and service main wheel and brakes | 1 | 1
re-install relieve tube, down hill flow now | 1 | 1
download all available manuf. tech bulletins, AD's etc | 2 | 2
inspect aircraft in accordance with an annual inspection,
Note: most of this was accomplished during re-finishing
This time includes rigging and paper work | 3 | 3
TOTAL FOR INSPECTION | 25.5 | 25.5
Trailer
remove old felt from fittings | 1 | 1
try to find new felt or similar - failed | 2 | 2
prepare - somewhat - to install new felt in fittings | 1 | 1
TOTAL FOR TRAILER | 4 | 4
MATERIALS | cost | units | $
Note:the following are good estimates and will be upgraded
at a later date
ABRASIVES
36/40 grit 8"discs boxes of 50 | 65 | 3 | 195
40 grit 6" discs boxes of 50 | 50 | 2 | 100
rolls of 80 grit 6" | 40 | 2 | 80
rolls of 2.75" 80 grit | 30 | 3 | 90
rolls of 2.75" 120 grit | 30 | 2 | 60
rolls of 2.75" 180 grit | 30 | 2 | 60
rolls of 2.75" 220 grit | 30 | 4 | 120
Sleeves of 220 w or dry | 30 | 2 | 60
Sleeves of 320 w or dry | 30 | 1 | 30
Sleeves of 400 w or dry | 30 | 1.5 | 45
Sleeves of 600 w or dry | 30 | 1.5 | 45
Sleeves of 2000 w or dry | 30 | 1.5 | 45
rubbing compound | 25 | 1 | 25
PAINTS, FILLERS AND PRIMERS
fillers, contouring compounds | 25 | 1 | 25
primers (2gal kits epoxy) | 75 | 3 | 225
finish coats (urethane) one gallon mixed incl hardener | 120 | 4 | 480
diluents for above | 40 | 1 | 40
solvents (acetone for cleaning guns hands etc) 55 gal drum | 200 | 0.5 | 100
DX 330 glue remover general cleaner | 30 | 1 | 30
Masking tapes and paper (all together estimate) |  |  | 50
TOTAL MATERIALS very close estimate |  |  | 1905
0
TOOLS WRITTEN OFF PER JOB |  | units
0
DA sander | 45 | 1 | 45
8" buffer sander | 160 | 0.5 | 80
sanding blocks |  |  | 30
0
TOTAL FOR TOOLS |  |  | 155
PURCHASED PARTS incl. shipping and handling |  |  | 0
0
rebuild TOST release | 195 | 1 | 195
all sealing tapes, zig zags for all controls (seems very high) |  |  | 300
cables nicopress sleeves etc |  |  | 25
misc. small hardware etc |  |  | 30
TOTAL PARTS |  |  | 550
END OF TIMESHEET
0