## Sheet1
Last update	Nov. 03/ 23

	WEEKS IN MONTHS		ALLOTTED TIMES					Nov					Dec					Jan					Feb					Mar					Apr					May					Jun					Jul					Aug					Sep					Oct					Nov					Dec					Jan					Feb					Mar					Apr					May					Jun					Jul					Aug					Sep					Oct					Nov					Dec
	scheduled	1	2	3	4	5	6	7	8		1	2	3	4		1	2	3	4		1	2	3	4		1	2	3	4		1	2	3	4		1	2	3	4		1	2	3	4		1	2	3	4		1	2	3	4		1	2	3	4		1	2	3	4		1	2	3	4		1	2	3	4		1	2	3	4			1	2	3	4		1	2	3	4		1	2	3	4		1	2	3	4		1	2	3	4		1	2	3	4		1	2	3	4		1	2	3	4		1	2	3	4		1	2	3	4		1	2	3	4		1	2	3	4

	FINISH SAILPLANE	A					F

Nov 23	INSTALL TRUSSES	A					G
	INSTALL PLASTIC	A					G
Nov 23
Nov 23	FINISH TOOL BOXES	A					A

Nov -Dec 23	CONTOUR BOWS	A	A	A	A					?	?	?		?

	WEATHER PROOF SHOP	A					W

	GLASS BOW STEP 1	A
	GLASS BOW STEP 2	A
	APPLY CORE 1
	APPLY CORE 2
	GLASS BOW STEP 1	A
	GLASS BOW STEP 4	A
	GLASS BOW STEP 5	A
	GLASS BOW STEP 6	A
	GLASS BOW STEP 7	A
	GLASS BOW STEP 8	A

	INSTALL BOW SEGMENT 1	A
	INSTALL BOW SEGMENT 2	A
	INSTALL BOW SEGMENT 3	A
	INSTALL BOW SEGMENT 4	A

	MOVE STERN	A
	FINISH STERN #1	A	A	A
	STERN 2 LAM #1	A
	STERN 2 CORE	A
	STERN 2 GLASS	A

	MAIN CON BEAM

	BOT CAPS INCL radii	A
	TOP CAPS incl radii	A
	SHEAR BEAMS	A	A
	ASSEMBLY	A	A
	CORE	A	A
	SHEAR GLASS	A	A

	TRANSOM

	GET READY	A	A	A
	LAMINATE BOT. CAP	A	A
	FAB SHEAR WEBS	A	A	A
	INSTALL SHEA WEBS	A
	L AMINATE TOP. CAP	A	A

	CABIN
	FAB RADII MOLD	A	A
	FAB RADII	A	A
	LAY OUT IN YARD	A
	STAND UP IN YARD	A
	ASSY. WITH RADII	A
	COVER WITH PLASTIC	A

	MOVE OUT OF HOUSE ++

	MINOR REPAIRS INSIDE	A	A	A	A
	MT TOOL TRAILER	A